## QueryInfo
BCV Defect Disposition Log 03_17 Release
Query URL: | https://sdp.web.att.com/rs2/query/17744/dataservice?limit=-1&basicAuthenticationEnabled=true&report=17735
Description: | Standard custom report created by TDP Reports Team. NOTE: Suggest using PRISM Project ID as input parameter.
See the QueryResults sheet for the query results.
What else can I do with this data?
• Create a pivot table or chart.
• Add this query to an existing workbook by using the query URL at the top of this sheet.

## QueryResults
Work Area | PRISM Project ID | ID (Work Item) | URL (Work Item) | Creation Date (Work Item) | Creator (Work Item) | Application Found In | Detected In Release | Planned Closing Release Deployment Date (M9) | Status (Work Item) | Resolution (Work Item) | Owner (Work Item) | Severity (Work Item) | Summary (Work Item) | EST Fixed Date | Priority (Work Item) | Defect Type | Resolved Date (Work Item) | Resolver (Work Item) | Planned Closing Release (Custom) (Work Item) | Phase Found In (Custom) (Work Item) | Comment Count (Work Item) | PMT (Custom) (Work Item) | Root Cause Application (Custom) (Work Item) | Root Cause Application SubTeam (Custom) (Work Item) | Root Cause Details (Custom) (Work Item) | Root Cause Phase (Custom) (Work Item) | Root Cause Reason (Custom) (Work Item) | Root Cause Role (Custom) (Work Item) | Root Cause, Root Cause Category (Custom) (Work Item) | Test Case ID | Test Case | URL (Test Case) | Application Fixed In SubTeam (Waterfall) (Custom) (Work Item)
Defect Management | 306622c | 877543 | https://sdp.web.att.com/ccm/resource/itemName/com.ibm.team.workitem.WorkItem/877543 | 3/9/20 3:13 PM | PRAKASH, PREM | Digital IDP:27531 | 2020.03.03 IDP Release |  | Retest Complete | Info not available | PRAKASH, PREM | Severity 2 | For AT&T TV, Rewards card price is displayed in Sticky bar ¦ ENV Tst3 |  | High | Defect |  | Unassigned | 2020.03.17 IDP Release | Integrated Systems Test (IST) | 19 | 485377 | Digital IDP:27531 |  |  | Phase 4: Install and Production Readiness Test | Code/Software Component | UAT - User Acceptance Test | Coding |  |  |  | Bundles Configuration & Validation
Defect Management | 306622c | 872649 | https://sdp.web.att.com/ccm/resource/itemName/com.ibm.team.workitem.WorkItem/872649 | 2/19/20 11:16 AM | AIDUDDI, VISHWANATH | Digital IDP:27531 | 2020.03.03 IDP Release |  | Retest Complete | Info not available | AIDUDDI, VISHWANATH | Severity 2 | For AT&T TV, Customer comes with Standalone AT&T TV Intent , adds TV package and when he clicks on Ckav on internet section and after ckav, focus shifts to channels TV Section , expectation is to have get the focus on internet section |  | Medium | Production Defect |  | Unassigned | 2020.03.17 IDP Release | Integrated Systems Test (IST) | 24 | 485377 | Digital IDP:27531 |  |  | Phase 4: Install and Production Readiness Test | Code/Software Component | UAT - User Acceptance Test | Coding |  |  |  | Bundles Configuration & Validation
Defect Management | 306622c | 877557 | https://sdp.web.att.com/ccm/resource/itemName/com.ibm.team.workitem.WorkItem/877557 | 3/9/20 3:49 PM | PRAKASH, PREM | Digital IDP:27531 | 2020.03.03 IDP Release |  | Cancelled | Cannot Reproduce | PRAKASH, PREM | Severity 2 | For AT&T TV, TV PKG is getting removed after BB address Validation in CVAV |  | High | Defect | 3/10/20 11:12 AM | PRAKASH, PREM | 2020.03.17 IDP Release | Integrated Systems Test (IST) | 2 | 485377 | Digital IDP:27531 |  |  | Phase 3: Design, Development and Pre-Production Testing | Root Cause Not Defined | Environment | Other |  |  |  | Bundles Configuration & Validation
Defect Management | 306622c | 875444 | https://sdp.web.att.com/ccm/resource/itemName/com.ibm.team.workitem.WorkItem/875444 | 2/28/20 4:10 PM | AIDUDDI, VISHWANATH | Digital IDP:27531 | 2020.03.03 IDP Release |  | Retest Complete | Info not available | AIDUDDI, VISHWANATH | Severity 3 | For AT&T TV, when we use referral url - Base package panel is in open state, if customer switch package, base package panel collapse but channels panel is not opening auto, customer has to manually click on edit and then panel opens |  | Low | Defect |  | Unassigned | 2020.03.17 IDP Release | Integrated Systems Test (IST) | 14 | 485377 | Digital IDP:27531 |  | code fix moved to dev2 | Phase 2: Requirements and Funding | Code/Software Component | Requirements | Coding |  |  |  | Bundles Configuration & Validation
Defect Management | 306622c | 876050 | https://sdp.web.att.com/ccm/resource/itemName/com.ibm.team.workitem.WorkItem/876050 | 3/3/20 10:58 AM | AIDUDDI, VISHWANATH | Digital IDP:27531 | 2020.03.03 IDP Release |  | Retest Complete | Info not available | AIDUDDI, VISHWANATH | Severity 3 | For AT&T TV, Add button Alignment issue on the base package |  | Low | Production Defect |  | Unassigned | 2020.03.17 IDP Release | Integrated Systems Test (IST) | 23 | 485377 | Digital IDP:27531 |  |  | Phase 4: Install and Production Readiness Test | Code/Software Component | UAT - User Acceptance Test | Coding |  |  |  | Bundles Configuration & Validation
Defect Management | 307878c | 878933 | https://sdp.web.att.com/ccm/resource/itemName/com.ibm.team.workitem.WorkItem/878933 | 3/13/20 12:58 PM | GHANTA, RAKSHITHA | Digital IDP:27531 | 2020.03.17 IDP Release |  | Retest Complete | Info not available | GHANTA, RAKSHITHA | Severity 1 | IDSE_PI7_ 307878c _tst3_Getting Gateway timeout |  | High | Defect |  | Unassigned | 2020.03.17 IDP Release | (SAFe) System Integration | 1 | 486471 | Digital IDP:27531 |  |  | Phase 3: Design, Development and Pre-Production Testing | Environment Setup - non-Database | Environment | Environment |  |  |  | IST
Defect Management | 307878c | 875852 | https://sdp.web.att.com/ccm/resource/itemName/com.ibm.team.workitem.WorkItem/875852 | 3/2/20 5:55 PM | GHANTA, RAKSHITHA | Digital IDP:27531 | 2020.03.03 IDP Release |  | Retest | Info not available | GHANTA, RAKSHITHA | Severity 2 | IDSE_PI7_ 307878c _Wireless_ UP_getting blank UP page after login |  | Medium | Production Defect |  | Unassigned | 2020.03.17 IDP Release | (SAFe) System Integration | 10 | 486471 | Digital IDP:27531 | Gateway | fixed the redirection logic | Phase 3: Design, Development and Pre-Production Testing | Application Design | Development | Design Specification |  |  |  | IST
Defect Management | 318667j | 879442 | https://sdp.web.att.com/ccm/resource/itemName/com.ibm.team.workitem.WorkItem/879442 | 3/16/20 8:50 PM | MOHAPATRA, PARTHA SARATHI | Digital IDP:27531 | 2020.03.17 IDP Release |  | Closed | Info not available | MOHAPATRA, PARTHA SARATHI | Severity 2 | ATT_TV_:Submit Order -Equipment-Pricing: - Pricing is not coming correctly in the PDF files of the RIA mails for the equipment's taken |  | Medium | Defect | 3/17/20 10:53 AM | MOHAPATRA, PARTHA SARATHI | 2020.03.17 IDP Release | Integrated Systems Test (IST) | 6 | 490664 | Digital IDP:27531 | OCE | After migration of correct OCE envt,its&nbsp; started&nbsp; working | Phase 3: Design, Development and Pre-Production Testing | Packaging | Environment | Deployment |  |  |  | IST
Defect Management | 318667j | 878658 | https://sdp.web.att.com/ccm/resource/itemName/com.ibm.team.workitem.WorkItem/878658 | 3/12/20 5:53 PM | MOHAPATRA, PARTHA SARATHI | Digital IDP:27531 | 2020.03.17 IDP Release |  | Closed | Info not available | MOHAPATRA, PARTHA SARATHI | Severity 2 | ATT_TV_:Submit Order -RIA Mail- RIA mail is not coming for the submit orders of both online and indirect partners |  | Medium | Defect | 3/16/20 9:26 PM | MOHAPATRA, PARTHA SARATHI | 2020.03.17 IDP Release | Integrated Systems Test (IST) | 15 | 490664 | Digital IDP:27531 | ACSI Triage | After migration to correct CSI,its started working. | Phase 3: Design, Development and Pre-Production Testing | Environment unavailable | Environment | Environment |  |  |  | IST